## Sheet1
Task | Target Date | Actual Finished Date | Incharge
Setup Github | 3rd Feb 2020 | 3rd Feb 2020 | All
Tasks Allocation | 3rd Feb 2020 | 3rd Feb 2020 | All
Data Cleaning
Train & Test Dataset | 5th Feb 2020 | 5th Feb 2020 | Boon Jun
Weather Dataset | 5th Feb 2020 | 5th Feb 2020 | Russell
Spray Dataset | 5th Feb 2020 | 5th Feb 2020 | Sathya
EDA
Train & Test Dataset | 7th Feb 2020 | 10th Feb 2020 | Boon Jun
Weather Dataset | 7th Feb 2020 | 10th Feb 2020 | Russell
Spray Dataset | 7th Feb 2020 | 10th Feb 2020 | Sathya
Data Merging | 10th Feb 2020 | 10th Feb 2020 | Wesley
Feature Engineering | 11th Feb 2020 | 11th Feb 2020 | Wesley
Modelling | 13th Feb 2020 | 13th Feb 2020 | Wesley, Russell
Cost-Benefit Analysis | 13th Feb 2020 | 12th Feb 2020 | Boon Jun, Sathya
Presentation Slides | 13th Feb 2020 | 13th Feb 2020 | Wesley, Russell, Boon Jun
Readme | 13th Feb 2020 | 13th Feb 2020 | Sathya